## Per Phase (GxP)
Process(es) | List Process in Scope
No more then 4 processes
Config lock
Validation
[5 empty] | Prep | Workshop | Config Iteration 1 |  |  | Config Iteration 2 |  |  | Final Config | Train the Trainer Prep & TTT |  |  |  | Go-live | Hypercare
Resource Role | Total Hrs | Rate | Total | Resource Role | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18
Project Manager | 116 | 150 | 17400 | Project Manager | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 12 | 0 | 0 | 0 | 0
Solution Architect | 68 | 150 | 10200 | Solution Architect | 8 | 32 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Technical Architect |  | 150 | 0 | Technical Architect | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Solution Consultant | 192 | 125 | 24000 | Solution Consultant | 8 | 32 | 12 | 12 | 24 | 12 | 12 | 24 | 8 | 8 | 8 | 8 | 8 | 16 | 0 | 0 | 0 | 0
Configuration Consultants | 268 | 60 | 16080 | Configuration Consultants | 0 | 0 | 40 | 40 | 20 | 40 | 40 | 0 | 40 | 16 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0
Validation Specialist | 136 | 125 | 17000 | Validation Specialist | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 16 | 24 | 24 | 24 | 16 | 16 | 8 | 0 | 0 | 0
Hypercare | 40 | 125 | 5000 | Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 10
Rollout Support | 0 | 125 | 0 | Rollout Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  |  | 89680

## Per Phase (Non-GxP)
Process(es) | List Process in Scope
No more then 4 processes
Config lock
[5 empty] | Prep | Workshop | Config Iteration 1 |  |  | Config Iteration 2 |  |  | Final Config | UAT Support / Train the Trainer Prep & TTT |  |  |  | Go-live | Hypercare
Resource Role | Total Hrs | Rate | Total | Resource Role | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18
Project Manager | 116 | 150 | 17400 | Project Manager | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 12 | 0 | 0 | 0 | 0
Solution Architect | 68 | 150 | 10200 | Solution Architect | 8 | 32 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Technical Architect | 0 | 150 | 0 | Technical Architect | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Solution Consultant | 200 | 125 | 25000 | Solution Consultant | 8 | 32 | 12 | 12 | 20 | 12 | 12 | 20 | 8 | 12 | 12 | 12 | 12 | 16
Configuration Consultants | 280 | 60 | 16800 | Configuration Consultants | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Validation Specialist | 0 | 125 | 0 | Validation Specialist | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hypercare | 40 | 125 | 5000 | Hypercare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 10
Rollout Support | 0 | 125 | 0 | Rollout Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  |  | 74400